## DFM Problems
Seeed Fusion Design for Assembly (DFA) report
| Order Number: | A1834381 |  |  |  | Date: | 2023-02-23
| Prepared by: | HLB |  |  |  | Last Updated: | 2023-02-23
Item | Problem Description | Reference/MPN |  | Impact | Image | Seeed Suggestion | Customer Feedback | Seeed Suggestion | Severity | Status
3 | The position of the component on the pad is repeated with other components | J8 | S2B-PH-SM4-TB(LF)(SN) | Soldering defects more likely and more difficult to repair (additional costs may be involved) |  | Please update the position of the component on the pad | I have removed the pads for X1. J8 remains in place. | Thank you for your response, if X1 being a useful connector, will influence the soldering, | High | Open

## Sheet1 (hidden)
| Problem Description |  | Impact |  | Suggestion | Severity | Status | Square length (mm) | Diagonal (mm) | Rectangle length
1 | We cannot find the part on the boards | 1 | Cannot solder the part | 1 | Please add the part designator to the Gerber files or assembly file | Low | Open | 0.5 | 0.70711 | x | y
2 | We do not have access to the part's footprint | 2 | We cannot verify the part's footprint |  | Please update the footprint to match the datasheet | Middle | Closed | 0.65 | 0.91924 | 0.5 | 0.3 | 0.5831
3 | The width of the pad is much larger than the datasheet | 3 | Soldering defects more likely and repairs may be necessary (additional costs may be required) |  | Please update the footprint to match the datasheet or change the part | High |  | 0.8 | 1.1314 | 0.6 | 0.4 | 0.72111
4 | The pad size appears to be 0805 but the part is size 1206 | 4 | Soldering defects more likely and more difficult to repair (additional costs may be involved) |  | Change the footprint to |  |  |  |  | 0.9 | 0.4 | 0.98489
5 | The pad size appears to be 0603 but the part is size 0805 | 7 | In our assembly experience, 0402 parts with pad spacing larger than 0.5mm will likely have soldering defects and require rework. |  | Send us the datasheet with the package details or confirm that the land pattern in the files is correct (we will not be held responsible for any assembly problems as a result)
6 | The pad size appears to be 0402 but the part is size 0603 |  | We cannot solder the part | 7 | Change the footprint to 0402 and decrease the pad spacing to 0.5mm or less
7 | This pad size appears to be 0402 size but the part size is 0603. Particularly, the distance between the pads is too large. | 9 | There may be some differences with the original MPN that may affect assembly | 8 | Decrease the pad spacing to 0.5mm or less
8 | The distance between the pads is too large for 0402 parts | 10 | We cannot verify the land pattern of the part | 9 | Could you send us the datasheet of the custom part or confirm that the original land pattern is ok?
9 | This customer supplied part appears to be labeled custom. Is it custom made? | 11 | Cannot machine assemble | 10 | Please tell us the manufacturer part number of this part and/or send us the datasheet
10 | This customer supplied part MPN does not appear to be correct | 12 | Additional wastage parts and assembly fees | 11 | Please provide the pick and place file. Please refer to this guide for help: https://support.seeedstudio.com/knowledgebase/articles/1911202-how-do-i-export-pcb-pick-and-place-xy-files-for
11 | No pick and place file |  | Cannot produce the boards | 12 | We suggest choosing another part with a larger footprint. Please send us the part number and update the Gerber files
12 | The part size is 0201. This will require machine assembly and require additional wastage parts | 16 | We do not know the correct orientation of the part | 16 | Please add a pin 1 mark to the silkscreen or assembly files
13 | The width of the pad is too small | 20 | Difficulty inserting the part for assembly | 17 | Please add a polarity indicator to the silkscreen or assembly files
14 | The footprint is too small | 23 | Otherwise, the part will not lie flat with the board | 18 | Please confirm the MPN or change the footprint
15 | The footprint is too large | 24 | Not enough parts to solder all boards | 24 | Please increase the size of the drill hole to match the datasheet
16 | There is no pin 1 indicator/mark |  |  | 25 | The cost for the extra parts to solder all boards comes to $ USD. To pay the additional fee, please follow the link below and change the quantity to 16 units, add it to your cart and checkout. Once paid, please tell me the payment order number (22xx xxxx xxxx): https://www.seeedstudio.com/Customized-order-payment-unit-for-fusion-p-455.html
17 | This part is polarised but there is no polarity mark in the files.
18 | The part is through-hole but the footprint is for a surface mount part
19 | The part is surface mount but the footprint is for a through-hole part
20 | The drill hole diameter is too small
21 | The drill hole is too small. The cross section of the pin is a square with length 0.5mm, so the diagonal length is √(0.5² + 0.5²) = 0.707mm. But the drill hole has a diameter of 0.8mm
22 | The drill hole is too small. The cross section of the pin is a square with length 0.64mm, so the diagonal length is √(0.64² + 0.64²) = 0.905mm. But the drill hole has a diameter of 0.8mm
23 | The drill hole is too small. The cross section of the pin is a square with length 0.8mm, so the diagonal length is √(0.8² + 0.8²) = 1.13mm. But the drill hole has a diameter of 0.8mm
24 | A portion of the part is supposed to hang over the edge of the PCB board
25 | The component quantities do not match the design. The BOM quantities should be multiplied by the number of boards on the panel.
26 | Tantalum/electrolytic capacitors are polarised, but there is no polarity mark in the files